## Sheet1
Epic | Actor | User Story | Acceptance Criteria | Estimation (Story Points) | Business Value | Priority | Sprint
Risk Profiling Questionnaire | Client | As a Client, I want to complete a mobile-friendly questionnaire so that my risk appetite can be assessed. | - Questionnaire loads quickly - Mobile responsive design - Mandatory fields validated | 3 | 1000 | High | Sprint 1
Risk Profiling Questionnaire | Client | As a Client, I want to save progress so that I can resume later. | - Save button available - Resume starts at last question - Data securely stored | 3 | 1000 | High | Sprint 1
Risk Profiling Questionnaire | Admin | As an Admin, I want to manage questionnaire questions so that I can keep it updated. | - Add/edit/remove questions - Question order adjustable - Changes reflected in real-time | 5 | 1000 | High | Sprint 1
Risk Profiling Questionnaire | Admin | As an Admin, I want to configure risk bands so that scores classify correctly. | - Define thresholds for Conservative, Moderate, Aggressive - Immediate application | 5 | 1000 | High | Sprint 1
Risk Profiling Questionnaire | Client | As a Client, I want clear instructions so that I understand why this questionnaire is needed. | - Instructions visible at start - Explanation of purpose provided | 2 | 500 | Medium | Sprint 1
Scoring Algorithm | API Consumer | As an API Consumer, I want to send responses so that I get back a client risk score. | - API accepts valid payload - Score returned correctly - Error for invalid requests | 3 | 1000 | High | Sprint 1
Scoring Algorithm | Admin | As an Admin, I want to update scoring weights so that the algorithm reflects policy changes. | - Weights editable via admin panel - Audit log of changes | 3 | 1000 | High | Sprint 1
Scoring Algorithm | API Consumer | As an API Consumer, I want documentation so that I can integrate easily. | - API docs available - Example requests/responses provided | 5 | 1000 | High | Sprint 1
Scoring Algorithm | System | As a System, I want to store score results so that historical analysis is possible. | - Store score securely - Link to client profile | 5 | 1000 | High | Sprint 2
Suitability Engine Logic | Wealth Advisor | As a Wealth Advisor, I want a list of suitable products so that I can recommend them to clients. | - Product list filtered by client risk profile - Sorted by relevance | 3 | 1000 | High | Sprint 2
Suitability Engine Logic | Compliance Officer | As a Compliance Officer, I want rules engine logs so that I can audit decisions. | - Logs available for review - Show rule applied for recommendation | 3 | 1000 | High | Sprint 2
Suitability Engine Logic | API Consumer | As an API Consumer, I want to query recommended products so that I can embed them. | - API endpoint provided - Response matches risk classification | 3 | 1000 | High | Sprint 2
Suitability Engine Logic | Wealth Advisor | As a Wealth Advisor, I want to view reasons for recommendations so that I can explain to clients. | - Reasons visible alongside products | 2 | 1000 | High | Sprint 2
API Development & Integration | API Consumer | As an API Consumer, I want secure API endpoints so that my integration is safe. | - OAuth2 required - TLS encryption enforced | 2 | 1000 | High | Sprint 2
API Development & Integration | API Consumer | As an API Consumer, I want consistent response formats so that parsing is simple. | - JSON standard format - Status codes used properly | 2 | 500 | Medium | Sprint 2
API Development & Integration | Admin | As an Admin, I want API access logs so that I can monitor usage. | - Logs show timestamp, caller, action | 2 | 1000 | High | Sprint 2
API Development & Integration | API Consumer | As an API Consumer, I want error codes explained so that I can troubleshoot easily. | - Documentation of all error scenarios | 3 | 1000 | High | Sprint 2
UI/UX | Client | As a Client, I want a simple and intuitive UI so that I can easily navigate. | - Clear layout - Large touch targets - Accessible font sizes | 3 | 1000 | High | Sprint 2
UI/UX | Advisor | As an Advisor, I want my dashboard clean and responsive so that I can quickly find client info. | - Load within 2 seconds - Mobile/tablet friendly | 3 | 1000 | High | Sprint 3
UI/UX | Client | As a Client, I want my answers auto-saved so that I don’t lose progress. | - Auto-save after each question - Resume restores state | 3 | 1000 | High | Sprint 3
Security & Compliance | Compliance Officer | As a Compliance Officer, I want audit trails so that I can verify all actions. | - Log user actions - Store timestamp, actor, action | 2 | 1000 | High | Sprint 3
Security & Compliance | Admin | As an Admin, I want role-based access so that only authorized users can make changes. | - Roles configurable - Permissions enforced at UI/API | 3 | 1000 | High | Sprint 3
Security & Compliance | Compliance Officer | As a Compliance Officer, I want secure storage of client data so that regulations are met. | - Encrypt at rest - Encrypt in transit | 3 | 1000 | High | Sprint 3
Reporting & Dashboard | Advisor | As an Advisor, I want dashboard reports of my clients so that I can monitor engagement. | - Report filters by date, risk profile - Summary charts | 3 | 1000 | High | Sprint 3
Reporting & Dashboard | Admin | As an Admin, I want usage stats so that I can track platform adoption. | - Daily/weekly usage summary | 2 | 1000 | High | Sprint 3
Reporting & Dashboard | Reporting User | As a Reporting User, I want export options so that I can download reports. | - Export to CSV, PDF - Maintain formatting | 2 | 1000 | High | Sprint 3
Reporting & Dashboard | Advisor | As an Advisor, I want client-level drill-down so that I can view details quickly. | - Click on summary → client detail view | 3 | 1000 | High | Sprint 3