## Sheet1
ID | Title | Type | Priority | Status | Estimation (Story Points) | Business Value | Sprint
NFR-1 | Questionnaire loads < 2 seconds under peak load | Non-functional requirement | High | Backlog | 3 | 1000 | Sprint 1
NFR-2 | Responsive UI across devices (mobile, tablet, desktop) | Non-functional requirement | High | Backlog | 5 | 1000 | Sprint 1
NFR-3 | Encrypt data at rest and in transit | Non-functional requirement | High | Backlog | 5 | 1000 | Sprint 1
NFR-4 | 99.9% API uptime target | Non-functional requirement | Medium | Backlog | 2 | 500 | Sprint 1
RISK-1 | Load testing before go-live | Risk mitigation | High | Backlog | 5 | 1000 | Sprint 2
RISK-2 | Fallback mechanism for 3rd party API failure | Risk mitigation | Medium | Backlog | 3 | 500 | Sprint 2
RISK-3 | Vulnerability scan before launch | Risk mitigation | High | Backlog | 5 | 1000 | Sprint 2
TD-1 | Refactor questionnaire UI code after MVP | Technical debt | Medium | Backlog | 3 | 500 | Sprint 3
TD-2 | Improve unit test coverage to 90% | Technical debt | Medium | Backlog | 3 | 500 | Sprint 3
ARCH-1 | Define API contract/specification (OpenAPI) | Architectural | Medium | Backlog | 2 | 500 | Sprint 3
ARCH-2 | Database schema design for risk profile storage | Architectural | High | Backlog | 5 | 1000 | Sprint 3
ARCH-3 | Design authentication/authorization mechanism (RBAC) | Architectural | High | Backlog | 5 | 1000 | Sprint 4
INF-1 | Setup staging environment | Infrastructure | High | Backlog | 5 | 1000 | Sprint 4
INF-2 | CI/CD pipeline setup for automated deployment | Infrastructure | Medium | Backlog | 3 | 500 | Sprint 4
INF-3 | Implement monitoring and logging tools | Infrastructure | Medium | Backlog | 3 | 500 | Sprint 4